## Work Plan and Timeline
TASKS AND ACTION ITEMS | TASK OWNER | START DATE | DUE DATE | DURATION | Status | Notes | MNot
Task Group: Space, Hotel, Logistics
Secure presentation room, executive session room, room for lunch, SVT report-writing room
Identify and block SVT/NSF/team members from outside NYC hotel
Order catering that is per-diem compliant
Identify and arrange dinner venue for Day 1 Dinner for SVT and NSF executive dinner on Day 1 and Day 2
Create guidelines for transportation from airport/train station to hotel and from hotel to SV location
Establish a hybrid AV plan
Identify and document information about wireless internet access (not Eduroam) to provide to the SVT
Review NSF list of site‑visit participants and accommodations
Confirm vendor arrangements, building access and fire‑drill schedule
Get clarity and arrange transport for SVT and NSF members for tours of labs
Task Group: People
Confirm which institutional leaders are required and permitted.
Confirm participants from CU and Partners
Confirm which students to attend to participate in poster session & SLC Meeting
Add relevant site visit invitations to all calendars
Confirm final attendance and update calendar invitations
Assign staff roles (escort, greeter, set‑up crew, wrangler, mic assistant, timer, floaters)
Plan for overnight questions if relevant
Task Group: Video
Task Group: Presentation Development
Prepare presentation: vision, strategic plan, major advances, EWD overview, innovation ecosystem, response to previous SVR
Prepare presentation: institutional config, management systems, equipment/facilities, financial budget, self-sufficiency plan
Prepare thrust presentations, testbed discussions, videos if applicable
Create slide structure
Prepare document with past CoD meeting dates/themes/outcomes for lead dean to present
Lock presentation sequence
Assign presenter leads and backups
Teams create draft presentations/decks (v1)
Conduct internal presentation reviews based on v1 of the decks
Lock down time for messaging training
Revise all presentations/decks (v2)
Schedule and hold team practice 1
Adjust content based on team practice 1
Schedule and hold team practice 2 as a Red Team review session -- include outside experts
Adjust content based on rehearsal outcomes
Schedule and hold a full run-through with all presenters. Stress-test Q&A responses during this time.
Finalize slides
Assign a moderator for all sessions with Q&A
Prepare template for ppt responses to SVT overnight questions
Organize lab tours
Organize poster session
Task Group: Operational Readiness
Full day logistical run through in run of show tab
Reconfirm room reservations
Reconfirm AV will be in attendance all day
Provide attendee list to security
Finalize catering counts
Prepare NSF Site Visit Team Member bios and talking points for team to reference
Draft and disseminate briefing materials for leadership
Prepare emergency supplies (Tylenol, markers, tape, chargers, lint roller, mints, allergy-friendly snacks, etc.)
Send reminder emails with logistics and attachments
Send final reminder emails with logistics and attachments
Prepare and print name tents and other printed materials
Deliver supplies to buildings and set up room signage
Create backup plans for illnesses, technology failures, weather disruptions, etc.
Conduct day‑before dry run in the venue
Task Group: Final Content Lock
Submit a digital copy of all presentation materials to NSF
Disseminate briefing materials to the ARCH team
Task Group: Execution
Arrive early each day
Set up rooms and AV
Place name tents and materials
Brief facilitators and staff
Keep strict time
Capture questions asked by NSF and take notes
Task Group: Post-Visit
Conduct internal debrief
Document NSF questions and signals
Assign follow-up actions if any are requested from NSF
Send permitted thank-you notes
Archive all materials and lessons learned
Collect reimbursement from the SVT and NSF for meals and provide receipts as appropriate

## Run of Show
THIS IS AN EXAMPLE. ADJUST YOURS AS NEEDED
Time | Session Name | Attendees | To Do | Outcomes
DAY 1
7:45 | Continental Breakfast | SVT, Agency Team | Arrange breakfast in Agency conference room | Informal networking and preparation for the day
8:15 | Welcome & Introductions | SVT, Agency Director, Key Agency Personnel, University Personnel | Agency Director prepares introductions | SVT oriented to Agency team and university leadership
8:30 | Overview of the Center | SVT, Director, Deputy Director | Prepare presentation: vision, strategic plan, major advances, EWD overview, innovation ecosystem, response to previous SVR | SVT understands Agency vision, strategic plan, progress on NSF Performance Criteria, and response to previous SVR weaknesses/threats
9:30 | Research Program Infrastructure | SVT, Leadership Team | Prepare presentation: institutional config, management systems, equipment/facilities, financial budget, self-sufficiency plan | SVT informed of management systems, facilities, budget allocation, and sustainability plan
10:30 | Research Program by Thrust (Part 1) | SVT, Research Leads | Prepare thrust presentations, testbed discussions, videos if applicable | SVT understands research goals, methodologies, progress, quality, state-of-the-art contributions, and integration across projects
12:00 | Lunch | SVT, Agency Team | Arrange lunch | Continued informal discussion and networking
13:00 | Research Program by Thrust (Part 2) | SVT, Research Leads | Continue thrust presentations, highlight integration across thrusts/institutions | SVT has comprehensive view of all research thrusts, testbed progress, and cross-thrust integration
14:30 | Test Beds and Lab Tours (Optional) | SVT, Students, Faculty | Arrange student demonstrations of equipment/testbeds/simulations | SVT observes hands-on research demonstrations and testbed capabilities
15:30 | EXECUTIVE SESSION #1 | SVT, NSF Staff ONLY | Provide private room for 40 minutes | SVT and NSF staff discuss initial impressions and areas requiring deeper investigation
16:15 | Poster Session | SVT, Students | Organize posters by research thrust, provide map, ensure student availability (minimum 1 hour) | SVT gains in-depth knowledge of specific projects; students demonstrate research understanding
17:30 | Day 1 Adjourn | All
18:00 | SVT Executive Dinner & Discussion | SVT, NSF Staff ONLY (Closed) | Arrange dinner venue, note on agenda | SVT synthesizes Day 1 observations and identifies areas for Day 2 focus
DAY 2
7:45 | Continental Breakfast | SVT, Agency Team | Arrange breakfast in Agency conference room | Preparation for Day 2 sessions
8:15 | Engineering Workforce Development Presentation | SVT, EWD Program Staff | Prepare presentation: EWD programs overview, role of supplemental support | SVT understands EWD goals, strategy, accomplishments, and funding sources addressing NSF Performance Criteria
9:15 | Closed Meeting with Agency Students | SVT, Undergraduate/Graduate Students, Post-docs ONLY | Student Leadership Council prepares SWOT analysis presentation (30-60 min session) | Student Leadership Council SWOT analysis presented; SVT assesses student value-added and satisfaction with Agency participation
10:30 | Meeting with Council of Deans | SVT, Lead Dean (in-person), Partner Deans (video ok) | Lead Dean must be physically present; prepare document with past CoD meeting dates/themes/outcomes | Institutional commitment confirmed; discussion of support, interdisciplinary policies, IP policies, space and facilities
11:30 | Innovation Ecosystem Presentation | SVT, Industrial/Innovation Program Director, Stakeholder Staff | Prepare presentation: collaboration strategy, tech transfer, IAB membership, funding, tech targets | SVT understands industry engagement strategy, technology transfer accomplishments, stakeholder involvement, and economic impact
12:30 | Lunch | SVT, Agency Team | Arrange lunch | Informal discussion
13:30 | Closed Meeting with Advisory Board | SVT, Advisory Board Members ONLY | Upload AB Meeting Minutes to SharePoint prior to SV; allow 1 hour | AB Meeting Minutes reviewed (date, location, attendees, agenda, key takeaways); SWOT analysis shared; SVT assesses AB engagement and value
14:30 | Closed Meeting with IPAB | SVT, IAB Members ONLY (not during lunch) | IAB prepares SWOT analysis; avoid individuals with paid affiliations to core/partner institutions | IAB SWOT analysis presented; progress on prior SWOT issues reviewed; SVT assesses industry value-added and engagement level
15:45 | Contingency/Additional Discussions | SVT, Agency Team as needed | Flexible time for additional topics | Any outstanding questions or topics addressed
16:30 | FINAL EXECUTIVE SESSION | SVT, NSF Staff ONLY | Provide room with projector (30-45 min); SVT develops list of issues/questions | List of major concerns, issues, and questions requiring clarification developed for leadership team
17:30 | Meeting with Agency Leadership Team | SVT, Agency Leadership Team | Address SVT concerns/questions (30-60 min, usually around dinner) | Agency addresses SVT concerns; responses will inform SVR recommendations
18:30 | SVT Executive Dinner & Discussion | SVT, NSF Staff ONLY (Closed) | Arrange dinner venue, note on agenda | SVT discusses findings and begins formulating recommendations
Evening | Agency Leadership Team Preparation | Agency Leadership Team | Prepare brief PowerPoint responses to SVT questions (limited slides, focus on dialog); prepare hard copies and electronic version | Brief, focused responses prepared for Day 3 morning dialog
DAY 3
7:30 | Continental Breakfast | SVT Only | Provide breakfast for SVT; Leadership team on-call in-person or via email | SVT prepares for final discussions
8:00 | Leadership Team Q&A (If needed) | SVT, Agency Leadership Team | Brief presentation of responses to Day 2 questions; active dialog format; provide hard copies | SVT major issues resolved through active dialog; final opportunity for clarification
9:00 AM - 4:00 PM | Site Visit Report (SVR) Writing | SVT, NSF Staff | Provide: wireless internet (instructions/passwords), projector, IT technician on-call, access to Agency Web Library site | Site Visit Report (SVR) drafted with findings, recommendations, and assessment of NSF Performance Criteria
16:30 | Departure to Airport | SVT | Arrange transportation | SVT departs
IMPORTANT NOTES:
Allow adequate time between sessions for room transitions
All executive sessions are CLOSED (SVT & NSF staff only)
Final agenda must be sent to Agency PD at least 1 week before visit
Draft agenda must be sent to Agency PD at least 6 weeks before visit
Upload Advisory Board Meeting Minutes to NSF SV SharePoint prior to SV

## Attendees
Confirmed? | First Name | Last Name | Title | Role | Advisor | Institution | Email | Poster | Need Hotel | Date of Arrival | Date of Departure | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Supplies List
Item | Quantity | Packed? | Notes | Column 1
Black rolling cart
Breath mints
Dental floss picks
Lint roller
Pocket tissues
Hand sanitizer
Hair ties
Stain removal pen
Safety pins
Disposable face masks
Notepads
Pens
Sticky notes
Paper clips
Binder clips
Color stickers, circles
Laser pointer or clicker
Glasses cleaner
Throat lozenges
Granola bars
Tylenol/Ibuprofen
Disinfectant wipes
A Tupperware box to hold everything
Command Strips bag
Tape Gun
Liquid IV
Multiport dock
Surge Protectors - Research Development owns 3
Surge Protectors - Antonia + Alexis's
batteries that are used in Tang's mouse, keyboard etc.
USB- c cables
Duct Tape
Columbia Engineering Table Cloth
coffee pods + milk for NSF from 832
Reserved Flags
Columbia Engineering Podium Flag
Name Tags/Box/Letter Dividers
Shipping Tape
Blue tape
Cords Kit
Sharpies
Sticky Name Tags
Clipboards

## Contact List
Name | Affiliation | Role | Email | Phone | Notes

## Pre-Day Checklist
PRE-DAY CHECKLIST ¦ Complete before arriving at the site visit venue
SECTION 1 — Date & Conflict Screening (as early as possible)
Checklist Item | Owner | Timing | Notes
☐ Check for national and religious holidays near proposed site visit dates | Planner | 12+ weeks out
☐ Check for daylight savings transitions that could affect travel/schedule | Planner | 12+ weeks out
☐ Check hotel blackout weeks near the dates | Planner | 12+ weeks out
☐ Check for major NYC events (UN General Assembly, Climate Week, Fashion Week, etc.) | Planner | 12+ weeks out
☐ Check for other known travel disruptions (marathons, transit shutdowns, etc.) | Planner | 12+ weeks out
☐ Confirm venue availability and get leadership sign-off before booking | Planner | 10+ weeks out | Leadership must be confident in choice before it's communicated to outside parties
☐ Confirm NSF requirements for venue before finalizing | Planner | 10+ weeks out | Venue finalization issues caused downstream problems with industry invitations
SECTION 2 — People & Access (4–6 weeks out)
Checklist Item | Owner | Timing | Notes
☐ Confirm all attendees and send calendar invitations (confirm address, not just title) | Planner | 6 weeks out | Consider using Eventbrite or structured calendar tool
☐ Confirm partner institution attendees are registered (deans, remote faculty, etc.) | Planner | 6 weeks out | Pitt dean did not attend prep meeting — establish required vs. optional attendance early
☐ Confirm required prep meeting attendance from all participants | Planner | 4 weeks out | Flag non-attendance to leadership for escalation
☐ Confirm which students will attend; include both CU and partner institution students | Planner | 4 weeks out
☐ Brief ALL student attendees (including remote/partner institution students) before Day 1 | Planner | 1–2 weeks out | Southern students were not briefed — do not leave this to the night before
☐ Obtain card access / building access for the Innovation Hub or venue for all team members | Planner | 3 weeks out | Significant lead time required — do not leave until the week of
☐ Submit attendee list to security well in advance | Planner | 1 week out | QR code issues arose from students arriving early without access
☐ Simplify building access instructions in attendee comms — make process seem manageable | Planner | 1 week out | Prior instructions made process seem more onerous than it was
☐ Set up Slack channel; onboard PIs and remote team members to the channel | Planner | 3 weeks out | Slack was great for PIs and remote folks — maximize this
☐ Assign a dedicated Slack monitor role for day-of | Planner | 1 week out | Zoom chat monitoring also needed — assign a person
☐ Confirm industry partner communications ownership (especially if staff transitions occurring) | Planner | 6 weeks out | Deema's departure caused gaps — keep templates on shared drive, not individual inboxes
SECTION 3 — Venue & IT (2–4 weeks out)
Checklist Item | Owner | Timing | Notes
☐ Confirm room reservations (presentation room, exec session room, lunch room, report-writing room) | Planner | 4 weeks out
☐ Assess venue AV capabilities: confirm Zoom/Teams can be installed on venue desktop | Planner / IT | 3 weeks out | Teams installation on Tang desktop required CUIT to be there — plan ahead
☐ Identify whether venue uses CUIT or SEAS IT — clarify who 'owns' the AV equipment | Planner / IT | 3 weeks out | CUIT would not agree to be on-site for duration of site visit — understand scope before booking
☐ Confirm hybrid AV setup: camera system, microphones, display, Zoom banner settings | Planner / IT | 3 weeks out | Tang camera system failed during Friday run-through — would not have been fixed if run-through was day-of
☐ Schedule tech run-through for the day BEFORE the site visit (not 2+ days before) | Planner / IT | Schedule early | Camera failure was caught because run-through was Mon SV / Fri prep — build this in as a rule
☐ Confirm Microsoft Teams / Zoom installation on venue desktop before run-through | IT | Before run-through | Requires CUIT to be present in person
☐ Test speaker notes display on venue desktop; test Zoom banner display | IT / Ops | During run-through | Both were issues — test explicitly
☐ Reboot venue desktop and re-test AV after each day | IT / Ops | Each morning | Tang desktop needed rebooting each day
☐ Confirm wireless internet access for SVT (non-Eduroam); document password and instructions | Planner | 1 week out
☐ Confirm coat room or coat rack arrangements; get vendor confirmation of setup | Planner | 1 week out | Coat rack issues required refund — confirm delivery and setup day-of
☐ Create and deliver wayfinding signs (bathrooms, entry/exit, registration) | Ops Team | Day before
☐ Confirm printer access nearest to the site — add to IT checklist | IT / Ops | Day before | Print run-of-show and speaker timing sheets at site
☐ Check that a presentation monitor is included in the supplies going to the venue | Ops Team | Day before
☐ Establish a business Uber account for last-minute logistics needs | Admin | Standing item | Needed for unexpected transportation day-of
SECTION 4 — Catering (2–3 weeks out)
Checklist Item | Owner | Timing | Notes
☐ Confirm catering headcount methodology — track 'optional' attendees separately | Planner | 3 weeks out | Significant optional attendance made headcount difficult to pin down
☐ Collect dietary restrictions from all attendees (celiac, gluten-free, allergies, etc.) | Planner | 3 weeks out | Celiac issue arose — collect this systematically via RSVP form
☐ Confirm venue or caterer can accommodate celiac/gluten-free needs | Planner | 3 weeks out | Have a list of celiac-safe restaurants nearby as backup
☐ Require food labels on all catering items (allergens, ingredients) | Planner / Caterer | Confirm with vendor
☐ Confirm per-diem compliance for all catering orders | Planner | Before ordering
☐ Confirm dinner venues for Day 1 and Day 2 executive dinners | Planner | 4 weeks out
☐ Complete catering order form (use standard template) | Planner / Jessie | 2 weeks out | Use Jessie's meal portal / payment form — ensure access ahead of time
☐ Stock: gum/breath mints, bottled water, coffee, milk | Ops Team | Day before | Gum and water were crowd favorites — stock more than you think you need
☐ Arrange Dino BBQ or equivalent team dinner if applicable | Planner | 1 week out
SECTION 5 — Presentations & Content (3–6 weeks out)
Checklist Item | Owner | Timing | Notes
☐ Confirm slide format with all presenters — test Google Slides → PowerPoint conversion early | Planner | 3 weeks out | Conversion caused formatting issues — confirm and test 48+ hours before site visit
☐ Define and align on key terminology (e.g., 'test bed') across all presentations | PI / Planner | 3 weeks out | Test bed definition confused reviewers — add a glossary slide or pre-brief reviewers
☐ Lock presentation sequence and assign presenter leads and backups | PI / Planner | 4 weeks out
☐ Prepare briefing materials for SVT members (bios, talking points) | Planner | 1 week out
☐ Prepare a template for PPT responses to overnight SVT questions | Planner | 2 weeks out
☐ Prepare printed timekeeper/speaker agenda (one per timekeeper) | Ops Team | Day before | Print name, time slot, session — keep it simple for the timekeeper
☐ Assign a Zoom/hybrid chat monitor for day-of Q&A sessions | Planner | 1 week out | Team needs to be more involved in Zoom chat — assign explicitly
☐ Prepare document format for capturing SVT questions day-of | Planner | 1 week out | Unexpected time crunch for questions — have format ready
☐ Disseminate briefing materials to the ARCH team | Planner | 1 week out
SECTION 6 — Name Tags & Printed Materials (1 week out)
Checklist Item | Owner | Timing | Notes
☐ Generate name tags using standard template; verify institutional abbreviations before printing | Ops Team | 1 week out | WashU was listed as 'University of Washington' — review all abbreviations
☐ Confirm name tag format: Avery 74541 or 5309 as applicable | Ops Team | 1 week out
☐ Explore AI-assisted name tag generation for large attendee lists | Planner | Ongoing | Action item from debrief — evaluate for next site visit
☐ Print run-of-show and speaker timing list for timekeeper | Ops Team | Day before
☐ Print attendee list for security and greeter | Ops Team | Day before
☐ Print and assemble any other day-of materials (agendas, table cards, etc.) | Ops Team | Day before | Table cards needed to be done earlier and communicated earlier
☐ Prepare and confirm room signage and wayfinding | Ops Team | Day before
SECTION 7 — Emergency Prep & Contacts (1 week out)
Checklist Item | Owner | Timing | Notes
☐ Build and distribute emergency contacts sheet (facilities, CUIT, SEAS IT, catering, security) | Planner | 1 week out | Worst-case-scenario contacts — include cell numbers
☐ Create backup plans for: illness, AV failure, weather disruption, last-minute no-shows | Planner | 1 week out
☐ Confirm fire drill schedule with venue and building management | Planner | 1 week out
☐ Confirm IT technician is on-call for duration of site visit (not just setup) | Planner / IT | 1 week out | CUIT was unwilling to be on-site — resolve this upfront or use SEAS IT
☐ Pack emergency supplies bag: Tylenol, mints, gum, chargers, stain pen, lint roller, masks | Ops Team | Day before | See Supplies List tab for full inventory

## Day of pre-set checklist
DAY OF PRE-SET CHECKLIST ¦ Complete before attendees arrive each day
SECTION 1 — Arrival & Room Setup (arrive 60–90 min before first session)
Checklist Item | Owner | Timing | Notes
☐ Arrive at venue 60–90 minutes before first session | Ops Team | Each morning
☐ Confirm Facilities completed overnight setup; if not, escalate immediately | Ops Team / Planner | On arrival | Facilities did not set up space at CS3 — Kyoko and Antonia had to do it themselves
☐ Verify coat rack delivery and setup; photograph if issues for potential refund claim | Ops Team | On arrival
☐ Set up all rooms: presentation room, exec session room, lunch area, SVT report-writing room | Ops Team | On arrival
☐ Place name tents, printed agendas, and table cards in correct seats | Ops Team | On arrival | Confirm table card placement was communicated early — this caused issues at CS3
☐ Place wayfinding signs at bathrooms, entry/exit, and registration desk | Ops Team | On arrival
☐ Place supplies on tables: notepads, pens, sticky notes, water | Ops Team | On arrival
☐ Place gum and mints at all presenter stations and breakout tables | Ops Team | On arrival | A big hit — stock generously
☐ Set up reserved flags and Columbia Engineering tablecloths | Ops Team | On arrival
☐ Confirm iPad is charged and ready | Ops Team | On arrival | Keep using the iPad — it was useful
SECTION 2 — AV & Tech Setup (each morning before first session)
Checklist Item | Owner | Timing | Notes
☐ Reboot venue desktop (Tang or equivalent) — do this every morning | IT / Ops | Each morning | Tang desktop required rebooting each day — make this automatic
☐ Confirm Microsoft Teams and Zoom are installed and launching correctly | IT | Each morning
☐ Test camera system: confirm it is live and displaying correctly for hybrid attendees | IT | Each morning | Tang camera failed during run-through — test explicitly each day
☐ Test microphone(s): lapel, handheld, and room mics as applicable | IT | Each morning
☐ Test Zoom banner display — confirm it is showing correctly and not cutting off content | IT | Each morning | Zoom banner display issues arose during presentations
☐ Test speaker notes display on venue desktop | IT | Each morning | Speaker notes were not displaying properly — verify before session 1
☐ Confirm presentation slides are loaded on venue desktop; test advance/clicker | IT / Presenter | Each morning
☐ Test presentation monitor is connected and displaying | IT | Each morning | Add presentation monitor to standing supplies list
☐ Confirm laptop/device connections and multiport dock are functional | IT | Each morning
☐ Locate nearest printer; confirm it is accessible to the team | IT / Ops | Each morning
☐ Confirm wireless internet password is displayed or distributed to SVT members | IT / Ops | Each morning
☐ Mouse and keyboard: replace batteries if sluggish; have spares on hand | IT | Each morning | Tang mouse and keyboard were noted as problematic
☐ Assign Zoom chat monitor for the day — confirm they have Zoom access | Ops / Staff | Each morning | Team needed to be more involved in Zoom chat monitoring
SECTION 3 — Staff Briefing (30 min before first session)
Checklist Item | Owner | Timing | Notes
☐ Brief all on-site staff: roles, positions, and expectations for the day | Planner | Each morning | Roles: escort, greeter, setup crew, wrangler, mic assistant, timekeeper, floaters
☐ Confirm timekeeper has printed speaker timing sheet and understands time signals | Planner | Each morning | Quy kept adjusting time on the fly — timekeeper needs a clear physical reference
☐ Confirm Slack channel is active; brief all staff on use for day-of coordination | Planner | Each morning
☐ Confirm Zoom chat monitor knows their role and has access | Planner | Each morning
☐ Review run-of-show for the day with all staff; flag any changes from prior day | Planner | Each morning
☐ Confirm emergency contacts sheet is accessible to all staff | Planner | Each morning
☐ Confirm business Uber account is accessible for last-minute logistics | Planner | Each morning
SECTION 4 — Catering & Food Setup (per meal / before session)
Checklist Item | Owner | Timing | Notes
☐ Confirm catering delivery time with vendor and assign a team member to receive it | Ops / Planner | Each meal
☐ Place food labels on all items — include allergen information | Ops Team | Before each meal | Celiac issue — do not skip labels
☐ Confirm celiac-safe and allergy-friendly options are clearly separated and labeled | Ops Team | Before each meal
☐ Restock water, gum, and mints throughout the day | Ops Team | Throughout day
☐ Confirm final headcount with caterer if there are last-minute changes | Planner | Morning of
☐ Set up coffee station: pods, milk, cups — stock from 832 if needed | Ops Team | Each morning
☐ Confirm lunch room is set up with table cards if assigned seating is used | Ops Team | Before lunch | Industry lunch invites — calendar event address vs. invitation was an issue
SECTION 5 — Session-by-Session During the Day
Checklist Item | Owner | Timing | Notes
☐ Keep strict time — timekeeper signals presenters at 5 and 2 minute warnings | Timekeeper | Each session
☐ Capture all SVT/agency questions in the designated document format | Notetaker | Each session | Have question document format ready before Day 1 — prepare during unexpected breaks
☐ Monitor Zoom chat and escalate questions/comments to session moderator | Zoom monitor | Each session
☐ Escort SVT members between rooms during transitions | Escort | Each transition
☐ Provide room for EXECUTIVE SESSION — clear all non-SVT/NSF personnel | Planner / Staff | As scheduled
☐ Photograph any signage, room layouts, or materials issues for post-debrief | Ops Team | As needed
☐ Log any day-of issues in running notes doc for debrief | Planner | Throughout day
SECTION 6 — End of Day / Strike
Checklist Item | Owner | Timing | Notes
☐ Collect any remaining printed materials, name tags, supplies from all rooms | Ops Team | End of each day
☐ Return any borrowed AV equipment or supplies to their storage location | Ops Team | End of each day
☐ Document overnight questions from SVT for leadership PPT prep | Planner / Notetaker | End of Day 1/2
☐ Brief leadership team on overnight question prep requirements and timeline | Planner | End of Day 1/2
☐ Restock supplies cart for the following day | Ops Team | End of each day
☐ Confirm catering for next day is confirmed and headcount is correct | Planner | End of each day
☐ Send a quick Slack debrief note to the team — flag issues for next morning | Planner | End of each day

## Sample Budget
Item | Amount | Project
Site Visit Supplies: Order #1 | 437.86 | ARCH
Site Visit Supplies: Order #2 | 112.52 | ARCH
Tang + Hirsh Total | 4000 | ARCH
Facilities Total | 2096.36 | ARCH
Catering Total | 14870.95 | ARCH
External Evaluator's Hotel at The George | 509.67 | ARCH
External Evaluator's Train | 147 | ARCH
Pointer order from Amazon | 206.97 | ARCH
Dinner | 154.19 | ARCH
Uber for Dean Bobick 3.4.26 | 63.45 | ARCH
Last minute coffee |  | ARCH
Last minute drinks |  | ARCH
Uber | 67.13 | ARCH
Uber | 31.94 | ARCH
Uber | 43.4 | ARCH
Coaching | 2000 | ARCH
Meghan's graphic design contract | 3000 | ARCH
TOTAL | 27741.44
Total | 55482.88